## Slide 1: Cost proposal
EY cost proposal to Conservation International, RFP 0032026
19 September 2026

## Slide 2: A fixed price, built bottom-up from the work
US$40,000
58 days
US$621
fixed price for the full scope over 12 weeks, all-inclusive of profit, fees and taxes, with no cost sought after award
of professional effort across six roles, each mapped to a named activity and then to one of the four deliverables
blended rate per day, derived from the effort model and the published ceiling rather than from a rate card

## Slide 3: The scope was sized to the budget, not the other way round.

## Slide 4: Professional fees by role
Role | Days | Rate US$ per day | Total US$
Engagement partner | 5 | 1,100 | 5,500
Engagement manager | 16 | 725 | 11,600
Senior consultant, business models and finance | 13 | 575 | 7,475
Consultant, research and analysis | 19 | 375 | 7,125
Adviser, destination branding | 3 | 900 | 2,700
Adviser, conservation and protected-area tourism | 2 | 800 | 1,600
Total professional fees | 58 |  | 36,000
The rate card is not among the inputs used to build this proposal, so nothing is claimed here about how these rates compare to it. [[TO CONFIRM: EY Africa rate card and internal approval of these rates.]]

## Slide 5: Direct costs, all four of them named and necessary
Line item | Unit | Qty | Unit price US$ | Total US$
Market reports, datasets and database access | Purchase | 4 | 350 | 1,400
Specialist translation of non-English primary sources | Word | 10,000 | 0.10 | 1,000
Interview transcription | Interview | 16 | 35 | 560
Report and presentation design and production | Hour | 16 | 65 | 1,040
Total direct costs |  |  |  | 4,000
No travel, accommodation or subsistence is included. The RFP states the assignment is desk-based and requires no travel.

## Slide 6: Effort and payment follow the four contractual deliverables
Deliverable | Week | Days | Share | % | US$
Inception report | 2 | 7 | 12% | 10% | 4,000
Draft situational analysis and best practice assessment | 5 | 19 | 33% | 30% | 12,000
Draft report and presentation on brand delivery models | 10 | 22 | 38% | 35% | 14,000
Final report, next steps and Terms of Reference | 12 | 10 | 17% | 25% | 10,000
Total |  | 58 | 100% | 100% | 40,000
No more than 10% sits on the inception report, as the RFP requires. Ninety per cent of the price is released only after CI has accepted substantive analysis.

## Slide 7: What the budget narrative has to explain, and does
The RFP requires an explanation of the basis of every cost element, so each line is justified against the work it buys.
  Partner days sit where partner time changes the answer: kick-off, the week 7 screening, the recommendation, the week 10 presentation and final sign-off.
  The consultant carries the largest day count because source verification and the 13 deep-dives are the largest single task.
  Activity Three is costed rather than absorbed: 4 of the 10 days on deliverable 4 cover the implementation path and the Terms of Reference.
  One consolidated CI comment round on each draft is carried inside the figures, because acceptance is the stated criterion for both.
  There is no contingency line. The price is fixed and scope risk sits with EY.

## Slide 8: Why this represents value, beyond being inside the ceiling
CI is not paying for the starting line
  EY completed the 31-benchmark scan before this proposal was written and at its own cost.
  That contribution is why a 58-day programme can carry 13 deep-dives, 16 interviews and four elaborated options.
Every line is auditable arithmetic
  Unit price times quantity, days mapped to named roles and then to the four deliverables, and a total that reconciles exactly.
  There is no lump sum standing in for a calculation.
Risk sits with EY, not CI
  The price is fixed and all-inclusive, and no cost can be added after award.
  Any transaction tax that proves chargeable is absorbed within the total rather than added to it.

## Slide 9: Tax treatment and the assumptions the price holds on
Taxes
  The expected treatment is that services supplied by a South African EY entity to CI, as a non-resident of South Africa, are zero-rated for South African VAT as exported services.
  That turns on CI's contracting entity and its country of registration, neither of which is stated in the RFP.
  [[TO CONFIRM: EY tax to confirm the VAT and withholding position.]]
Assumptions
  Desk-based with no travel, and all interviews and presentations run virtually.
  CI supplies the list of 15 priority areas and the stakeholder contacts at inception, and brokers introductions in week 1.
  One consolidated comment round on each draft, within the agreed windows.
  Deliverables in English; the stakeholder presentation delivered twice, both virtually.

## Slide 10: Boilerplate
EY refers to the global organization, and may refer to one or more, of the member firms of Ernst & Young Global Limited, each of which is a separate legal entity. Ernst & Young Global Limited, a UK company limited by guarantee, does not provide services to clients. Information about how EY collects and uses personal data and a description of the rights individuals have under data protection legislation are available via ey.com/privacy. EY member firms do not practice law where prohibited by local laws. For more information about our organization, please visit ey.com.
Business Consulting | Sustainability and development advisory
© 2026 [[TO CONFIRM: EY member firm legal entity name]].
All Rights Reserved.
[[TO CONFIRM: document code]]
[[TO CONFIRM: ED code]]
ey.com
EY | Building a better working world
EY is building a better working world by creating new value for clients, people, society and the planet, while building trust in capital markets.
Enabled by data, AI and advanced technology, EY teams help clients shape the future with confidence and develop answers for the most pressing issues of today and tomorrow.
EY teams work across a full spectrum of services in assurance, consulting, tax, strategy and transactions. Fueled by sector insights, a globally connected, multidisciplinary network and diverse ecosystem partners, EY teams can provide services in more than 150 countries and territories.
All in to shape the future with confidence.